## Fields
field_id | field_name | block | crop | season | is_active | target_qty_per_week
F001 | Field A | North Block | Tomato | March 2026 | TRUE | 5000
F002 | Field B | South Block | Pepper | March 2026 | TRUE | 3200
F003 | Field C | East Block | Cucumber | March 2026 | TRUE | 4500
F004 | Field D | West Block | Lettuce | March 2026 | TRUE | 6000
F005 | GH-1 | Greenhouse 1 | Mixed Herbs | March 2026 | TRUE | 8000

## Weekly_Planting
week_number | week_label | season | field_id | field_name | block | crop | planned_date | actual_date | labor_cost | qty_planted | target_qty | notes
1 | Week 1 | March 2026 | F001 | Field A | North Block | Tomato | 2026-03-03 | 2026-03-03 | 3500 | 4800 | 5000
1 | Week 1 | March 2026 | F002 | Field B | South Block | Pepper | 2026-03-03 | 2026-03-03 | 2800 | 2300 | 3200 | Late start
1 | Week 1 | March 2026 | F003 | Field C | East Block | Cucumber | 2026-03-03 | 2026-03-03 | 5000 | 4200 | 4500
1 | Week 1 | March 2026 | F004 | Field D | West Block | Lettuce | 2026-03-03 | 2026-03-10 | 4500 | 3400 | 6000 | 1 week behind
1 | Week 1 | March 2026 | F005 | GH-1 | Greenhouse 1 | Mixed Herbs | 2026-03-03 | 2026-03-10 | 5500 | 7000 | 8000
2 | Week 2 | March 2026 | F001 | Field A | North Block | Tomato | 2026-03-10 | 2026-03-10 | 3500 | 4900 | 5000
2 | Week 2 | March 2026 | F002 | Field B | South Block | Pepper | 2026-03-10 | 2026-03-10 | 2800 | 2450 | 3200
2 | Week 2 | March 2026 | F003 | Field C | East Block | Cucumber | 2026-03-10 | 2026-03-10 | 5000 | 4300 | 4500
2 | Week 2 | March 2026 | F004 | Field D | West Block | Lettuce | 2026-03-10 | 2026-03-17 | 4500 | 3500 | 6000 | Still behind
2 | Week 2 | March 2026 | F005 | GH-1 | Greenhouse 1 | Mixed Herbs | 2026-03-10 | 2026-03-10 | 5500 | 7100 | 8000
3 | Week 3 | March 2026 | F001 | Field A | North Block | Tomato | 2026-03-17 | 2026-03-17 | 3500 | 4850 | 5000
3 | Week 3 | March 2026 | F002 | Field B | South Block | Pepper | 2026-03-17 | 2026-03-24 | 2800 | 2400 | 3200 | 1 wk behind
3 | Week 3 | March 2026 | F003 | Field C | East Block | Cucumber | 2026-03-17 | 2026-03-17 | 5000 | 4350 | 4500
3 | Week 3 | March 2026 | F004 | Field D | West Block | Lettuce | 2026-03-17 | 2026-04-07 | 4500 | 3600 | 6000 | 3 wks behind
3 | Week 3 | March 2026 | F005 | GH-1 | Greenhouse 1 | Mixed Herbs | 2026-03-17 | 2026-03-24 | 5500 | 7200 | 8000 | 1 wk behind

## Thresholds
kpi_name | green_max | orange_max | unit | description
cost_per_seedling | 2.5 | 3.5 | R | Cost per seedling in Rands
qty_achievement_pct | 95 | 80 | % | Actual qty as % of target
weeks_behind | 0 | 1 | weeks | Weeks behind planting schedule