## Cost_Per_Seedling
Week | Date | Weekly Labor Cost (R) | Qty Seedlings Planted | Cost per Seedling (R) | Status
Week 1 | 2024-01-01 | 9116.11 | 4132
Week 2 | 2024-01-08 | 9741.05 | 3073
Week 3 | 2024-01-15 | 13858.02 | 3560
Week 4 | 2024-01-22 | 9150.63 | 4491
Week 5 | 2024-01-29 | 8782.81 | 3612
Week 6 | 2024-02-05 | 9357.75 | 4086
Week 7 | 2024-02-12 | 13482.84 | 3188
Week 8 | 2024-02-19 | 10768.65 | 5019
Week 9 | 2024-02-26 | 11007.01 | 5613
Week 10 | 2024-03-04 | 9526.78 | 5319
Week 11 | 2024-03-11 | 12282.32 | 4478
Week 12 | 2024-03-18 | 12619.24 | 5744

## Planting_Programme
Week | Planned Date | Actual Date | Weeks Behind | Status
Week 1 | 2024-01-01 | 2024-01-01 | 0
Week 2 | 2024-01-08 | 2024-01-08 | 0
Week 3 | 2024-01-15 | 2024-01-22 | 1
Week 4 | 2024-01-22 | 2024-01-22 | 0
Week 5 | 2024-01-29 | 2024-02-12 | 2
Week 6 | 2024-02-05 | 2024-02-26 | 3
Week 7 | 2024-02-12 | 2024-02-19 | 1
Week 8 | 2024-02-19 | 2024-02-19 | 0
Week 9 | 2024-02-26 | 2024-03-25 | 4
Week 10 | 2024-03-04 | 2024-03-04 | 0
Week 11 | 2024-03-11 | 2024-03-18 | 1
Week 12 | 2024-03-18 | 2024-04-01 | 2

## Actual_vs_Target
Week | Date | Target Qty | Actual Qty | Achievement (%) | Status
Week 1 | 2024-01-01 | 5000 | 4750
Week 2 | 2024-01-08 | 5000 | 5100
Week 3 | 2024-01-15 | 5000 | 3900
Week 4 | 2024-01-22 | 5000 | 4400
Week 5 | 2024-01-29 | 5000 | 3250
Week 6 | 2024-02-05 | 5000 | 5500
Week 7 | 2024-02-12 | 5000 | 4650
Week 8 | 2024-02-19 | 5000 | 4250
Week 9 | 2024-02-26 | 5000 | 3600
Week 10 | 2024-03-04 | 5000 | 4950
Week 11 | 2024-03-11 | 5000 | 4400
Week 12 | 2024-03-18 | 5000 | 5200

## Dashboard_Summary
PLANTING KPI DASHBOARD
KPI | Latest Value | Status
Cost per Seedling (latest week)
Weeks Behind Programme (latest)
Achievement % (latest week)
ALERT THRESHOLDS
Cost per Seedling: GREEN <= R2.50 ¦ ORANGE <= R3.50 ¦ RED > R3.50
Planting Programme: GREEN = on time ¦ ORANGE = 1 week behind ¦ RED = 2+ weeks behind
Achievement %: GREEN >= 90% ¦ ORANGE >= 75% ¦ RED < 75%