## Weekly_Planting
week_number | week_label | season | field_id | field_name | block | crop | planned_date | actual_date | labor_cost | qty_planted | target_qty | notes
4 | Week 4 | March 2026 | F001 | Field A | North Block | Tomato | 2026-03-24 | 2026-03-24 | 3500 | 4900 | 5000
4 | Week 4 | March 2026 | F002 | Field B | South Block | Pepper | 2026-03-24 | 2026-03-24 | 2800 | 2600 | 3200 | Caught up
4 | Week 4 | March 2026 | F003 | Field C | East Block | Cucumber | 2026-03-24 | 2026-03-24 | 5000 | 4400 | 4500
4 | Week 4 | March 2026 | F004 | Field D | West Block | Lettuce | 2026-03-24 | 2026-03-31 | 4500 | 4000 | 6000 | 2 wks behind
4 | Week 4 | March 2026 | F005 | GH-1 | Greenhouse 1 | Mixed Herbs | 2026-03-24 | 2026-03-24 | 5500 | 7800 | 8000